## Sheet1
ID | Reporter | Assigned To | Priority | Severity | Product Version | Date Submitted | Updated | Summary | Status | Resolution | Reviewer 1 | Reviewer 2 | Accept 1 | Accept 2 | Importance 1 | Importance 2 | Effort 1 | Effort 2 | Type 1 | Type 2 | To address 1 | To address 2 | Comment
921 | Scott Little, Alan Carlin | Scott Little | normal | major |  | 2005-10-27 | 2011-03-07 | Semantics of "calling subroutines on match of a sequence" is not well defined. | assigned | open | Anupam | Ed | no | yes |  | high |  | 7 |  |  |  | yes | not convinced that the semantics for match_item are not well defined (Anupam)
966 | Brad Pierce | Ed Cerny | normal | feature |  | 2005-11-13 | 2010-05-13 | $isunbounded() | assigned | open | Ed | Shalom | yes | yes | nice | nice | 2 |  |  | Clarification | no | no | This Mantis should only fix minor textual issues brought up here, and the rest should be handled by 0001350.
1296 | John Havlicek | Dmitry Korchemny | normal | major |  | 2006-01-09 | 2011-03-07 | Annex E does not cover all clocked derived forms | assigned | open | Manisha | Ed |  | no |  | high |  | 14 |  |  |  | no | Not sure. (Manisha)
1502 | Dmitry Korchemny | Dana Fisman | normal | text |  | 2006-06-15 | 2011-03-07 | Decision point definition | assigned | open | Samik | Manisha |  | no | [7 empty] | no | Looks like a lot of effort. Not sure if we have enough time to address this.
1551 | Dmitry Korchemny | Dmitry Korchemny | normal | minor |  | 2006-08-01 | 2006-11-30 | Make disable iff sampled | assigned | open | Dmitry | Erik | no | no | low | low | 0.1 | 10 | Enhancement | Enhancement | yes | no
1853 | Brad Pierce | Ed Cerny | normal | feature |  | 2007-06-06 | 2011-03-04 | BNF for calls to $rose and other sample value system functions | assigned | open | Manisha | Shalom | yes | yes | high | low |  | 1 |  | Errata | yes | no | Can be done, but not important
2248 | Neil Korpusik | Scott Little | normal | minor | P1800-2008/D4 | 2008-01-25 | 2011-12-14 | "leading clock" - Champions feedback - items related to Mantis item 1683 | assigned | open | Ed | Manisha | yes | yes | nice | nice | 7 |  |  |  | yes | yes | Need to add references at few places
2255 | Lisa Piper | Manisha Kulshrestha | normal | minor | P1800-2008/D4 | 2008-01-29 | 2010-06-28 | clarifications on expect | assigned | open | Manisha | Ben |  | yes |  | low |  | 2 |  | Enhancement |  | yes
2340 | Lisa Piper | Tapan Kapoor | low | minor | P1800-2008/D4 | 2008-03-25 | 2010-06-28 | clarifications needed on vpi_control for non-temporal and immediate assertions | assigned | open | Manisha | Samik | yes | [7 empty] | yes
2367 | Jonathan Bromley | Dmitry Korchemny | normal | text | P1800-2008/D4 | 2008-04-23 | 2011-03-04 | Clarification: sampled-value functions are unaffected by disable-iff | assigned | open | Dmitry | Mehbub | no |  | low |  | 0.1 |  | Clarification |  | yes
2384 | John Havlicek | Scott Little | normal | minor |  | 2008-05-12 | 2011-03-04 | Rules about sampling for clocking block variables referenced in concurrent assertions are not clear | assigned | open | Anupam | Samik | no | [9 empty] | Sec 16.5.1 (IEEE1800-2012) defined sampling for clocking block variables
2546 | Shalom Bresticker | Scott Little | normal | minor | P1800-2009/D8 Ballot | 2008-12-28 | 2011-03-04 | empty match' and 'vacuous success' are not clearly defined in LRM | assigned | open | Shalom | Samik | yes |  | nice |  | 1 |  | Clarification |  | yes |  | The simplest way to handle this, even if not the best, is to add a reference to F.4.2 at the first use of 'empty match', in 16.8.2, and to add a reference to 16.14.8 (no longer 16.15.8) at the first use of 'vacuous success', in 16.14.3.
2555 | John Havlicek | Scott Little | normal | minor | P1800-2009/D8 Ballot | 2009-01-05 | 2011-03-04 | Clarify relationships of different local variable binding mechanisms | assigned | open | Anupam | Ed | yes | no | high | low |  |  | Errata |  |  | no | done (Ed). Resolution probably only requires deleting a line from the LRM (Anupam)
2560 | Dmitry Korchemny | user199 | normal | text | P1800-2009/D8 Ballot | 2009-01-08 | 2011-03-04 | Inconsistent description of conditional property operators | assigned | open | Ed | Mehbub | no |  | low | [5 empty] | no |  | vacuity defines it
2752 | user199 | user199 | normal | minor | P1800-2009/D8 Ballot | 2009-05-25 | 2011-03-04 | P1800-2009 Checker: Clarification on use of automatic variables in "blocks" | assigned | open | Ed | Manisha | no | no | low | [5 empty] | no |  | N/A. The language having a problem is already fixed in 2012. Should close the issue.
2810 | user199 | user199 | normal | minor | P1800-2009/D9 Recirc | 2009-07-15 | 2011-03-04 | Checker instantiation in an always or initial procedure | assigned | open | Dmitry | Manisha | no | no | low |  | 0.1 |  |  |  | yes |  | N/A. Should close it as not relevant anymore as checkers cannot be instantiated in procedural block of another checker
2825 | user199 | user199 | normal | minor | P1800-2009/D9 Recirc | 2009-07-23 | 2010-06-29 | 16.16 Disable iff: checkers not included in list of default extensions | assigned | open | Ed | Mehbub | yes |  | high |  | 2 |  |  |  | yes
2842 | Dmitry Korchemny |  | normal | minor | P1800-2009/D9 Recirc | 2009-08-09 | 2009-08-09 | Checker variable randomization with deferred assumptions is not defined | new | open | Dmitry | Anupam | yes | yes | nice | nice | 4 |  | Errata |  | yes | no | Because of lack of time for this PAR (Anupam)
2858 | user199 |  | normal | major | P1800-2009/D9 Recirc | 2009-08-24 | 2010-04-27 | Clarify the rules for assigning a value to a non-checker variable from within a checker | new | open | Dmitry | Manisha | no | yes | low |  | 0.1 |  |  |  | yes | yes | N/A. Need to add statements to clarify things.
2891 | user199 | user199 | normal | minor | P1800-2009/D9 Recirc | 2009-09-24 | 2011-03-04 | 17.3.1 Clarification on procedural concurrent assertions upon instantiation of checker | assigned | open | Dmitry | Anupam | no | no | low |  | 0.1 |  |  |  | yes |  | N/A. Sec 17:3 (IEEE1800-2012) has an example to clarify this case.
2939 | Surya Pratik Saha | Dmitry Korchemny | normal | minor | 1800-2009 | 2010-01-05 | 2014-11-27 | Hierarchical reference of checker variable should be disallowed completely | assigned | open | Anupam | Samik | yes |  | high | [5 empty] | yes |  | Resolution probably requires modifying a line in the LRM
2947 | user199 | user199 | normal | major | 1800-2009 | 2010-01-19 | 2011-03-04 | Module variables from within function or task not sampled, LRM and practice contradictory | assigned | open | Anupam | Erik | no | yes |  | high |  | 2 |  | Clarification |  | yes | 16.5.1 (last para) clarifies how to get sampled value of an expression which has function calls.
2980 | John Havlicek | Scott Little | normal | minor | 1800-2009 | 2010-02-15 | 2011-03-04 | semantic inconsistency between expect and procedural concurrent assertions | assigned | open | Samik | Manisha |  | yes |  | high | [6 empty] | This is something which may cause backward incompatibility so should address it now if we really want to address it.
3027 | Erik Seligman | Manisha Kulshrestha | normal | major | 1800-2009 | 2010-04-08 | 2011-03-04 | $asserton doesn't report existing failures in immediate assertions: should the language require it to? | assigned | open | Erik | Manisha | yes | yes | nice | nice | 5 |  | Enhancement |  | no | yes
3059 | John Havlicek | Scott Little | normal | minor | 1800-2009 | 2010-04-27 | 2011-03-04 | Study PSL local variables and determine if any alignment is warranted. | assigned | open | Samik | Mehbub
3099 | Dana Fisman | Dana Fisman | normal | major |  | 2010-05-23 | 2011-03-04 | action block triggering is not well defined | assigned | open | Anupam | Samik | no | [9 empty] | - I don't think I understand the issue here - pass (vacuous or not) and fail of an attempt of an assertion is well defined (Anupam)
3117 | Manisha Kulshrestha | Manisha Kulshrestha | normal | minor | 1800-2009 | 2010-06-15 | 2010-06-22 | make it clear that rewriting algorithm (F.4.1) applies to checker and let | assigned | open | Manisha | Shalom | yes | yes |  | nice |  | 1 |  | Clarification | yes | yes | easy
3147 | John Havlicek | Scott Little | normal | minor | 1800-2009 | 2010-07-14 | 2011-03-04 | Rule c) in 16.17 conflicts with the relaxed rules on clocking of assertions with inferred leading clocking event. | assigned | open | Ed | Anupam | yes | yes | high | nice |  | 1 |  |  | yes | yes | proposal will need to be updated with the current sec number
3217 | Surrendra Dudani | Ed Cerny | normal | major | 1800-2009 | 2010-09-29 | 2011-03-04 | Definition for referring to an assertion as a relative hierarchical name is missing in Section 23.6 | assigned | open | Ed | Mehbub | yes |  | must |  | 7 |  |  |  | yes
3478 | user199 |  | normal | major | 1800-2012 | 2011-04-01 | 2014-12-04 | Make drivers of inout ports accessible | new | open | Shalom | Ben | yes | no | nice | low |  |  | Enhancement | Enhancement | no | no | much opposition, hard to pass
3552 | Ben Cohen |  | normal | minor | P1800-2012/D1 | 2011-05-10 | 2011-06-21 | 16.14.6 Sequence methods // .triggered need further clarification | new | open | Ben | Samik | yes |  | high |  | 3 |  | Clarification |  | yes
3559 | Dmitry Korchemny |  | normal | minor |  | 2011-05-15 | 2011-06-03 | Implication example explanation is not accurate | new | open | Dmitry | Erik | yes | yes | high | high | 0.1 | 0.5 | Errata | Errata | yes | yes
3610 | Dmitry Korchemny |  | normal | major |  | 2011-06-14 | 2011-06-14 | Sequence methods with sequences admitting empty match | new | open | Ed | Anupam | yes | yes | high | nice | 1 |  |  |  | yes | yes | Resolution should be straight forward if we agree that we shouldn't allow methods on a sequence admitting empty match
3614 | Dmitry Korchemny | Dmitry Korchemny | normal | minor |  | 2011-06-15 | 2011-06-15 | Free variable randomization with assumptions with various clock domains | assigned | open | Dmitry | Anupam | yes | yes | high | nice | 2 |  |  |  | yes | yes | proposal is already in place.
3672 | Ed Cerny |  | normal | major | P1800-2012/D1 | 2011-07-13 | 2011-07-13 | hierarchical access to named block in assertion action blocks | new | open | Ed | Shalom | yes | yes | must | high | 3 |  |  |  | yes | yes | Should be done, but may be a lot of work
3924 | Erik_Seligman |  | normal | minor | P1800-2012/D3 | 2011-11-14 | 2011-11-14 | Need to clarify behavior when sequence event used as property clocking | new | open | Erik | Ben | yes | yes | high | high | 4 | 4 | Clarification | Clarification | yes | yes
3928 | Erik_Seligman |  | normal | minor | P1800-2012/D3 | 2011-11-16 | 2011-11-16 | Fix text in LRM encouraging incorrect coding of "clk iff enable" | new | open | Erik | Shalom | yes | yes | high | nice | 0.1 | 1 | Clarification | Clarification | yes | yes | LRM is not a methodology document
3935 | Laurence Bisht |  | normal | minor |  | 2011-11-21 | 2011-11-27 | rewriting algorithm. | new | open | Mehbub | Samik
4020 | Dmitry Korchemny |  | normal | minor |  | 2012-01-22 | 2014-08-05 | Syntax description of properties in inconsistent | new | open | Dmitry | Erik | yes | yes | nice | nice | 0.5 | 0.1 |  | Errata | yes | yes
4022 | Dmitry Korchemny |  | normal | minor |  | 2012-01-22 | 2012-01-22 | Bad style assertion failure reporting in 16.14.2 Assume statement | new | open | Dmitry | Mehbub | yes |  | nice |  | 0.5 |  |  |  | yes
4037 | Ben Cohen |  | urgent | minor | P1800-2012/D4 | 2012-02-09 | 2012-02-13 | Define false vacuity and contributions to pass/fail counters in simulation | new | open | Ben | Samik | yes |  |  | high |  | 2 | Clarification |  | yes
4041 | Daniel Mlynek |  | normal | minor | 1800-2009 | 2012-02-14 | 2014-11-27 | $fatal is used incorrectly in examples in LRM | new | open | Erik | Ben | yes | yes | high | high | 0.1 | 1 | Errata | Errata | yes | yes
4154 | Ben Cohen |  | normal | minor | P1800-2012/D5 | 2012-05-11 | 2015-11-04 | Errata in section 17, checker | new | open | Ben | Manisha | yes | yes | high | nice | 1 |  | Errata |  | yes | yes | Only first issue mentioned needs a fix. The second one is optional as it is not really an error. The third is already fixed
4173 | Ben Cohen |  | normal | minor | P1800-2012/D5 | 2012-05-23 | 2014-11-27 | 16.12, 17.3 clarify that range is bounded by constant expression | new | open | Ben | Mehbub | yes |  | high |  | 1 |  | Clarification |  | yes
4183 | Dmitry Korchemny |  | normal | minor |  | 2012-06-07 | 2012-06-10 | Returned value of sampled value functions should well-defined | new | open | Erik | Ben | yes | yes | high | high | 0.2 | 1 | Errata | Errata | yes | yes
4201 | Dana Fisman |  | normal | minor |  | 2012-06-26 | 2014-06-27 | Missing info with regard to untyped formal arguments | new | open | Anupam | Ed | no | yes |  | nice |  | 1 |  |  |  | no | Tools should automatically flag error is the expression is not valid. Example of sequence method used - remember 'triggered' is a valid method of 'event' type also.
4557 | Robert Liu |  | normal | trivial | 1800-2012 | 2013-04-25 | 2013-04-28 | Typos in clause 16 | new | open | Erik | Ben | yes | yes | high | high | 0.1 | 0.1 | Errata | Errata | yes | yes
4724 | Dmitry Korchemny |  | normal | minor |  | 2013-08-16 | 2013-08-18 | Checkers should be mentioned in the description of Reactive region | new | open | Dmitry | Mehbub | yes |  | high |  | 0.5 |  | Errata |  | yes
4750 | Dmitry Korchemny |  | normal | minor | 1800-2012 | 2013-09-27 | 2013-11-02 | Allow immediate assertions in checker body | new | open | Dmitry | Anupam | yes | no | must | low | 2 | 2 | Errata |  | yes | no | Resolution will require defining restrictions in static checker instances.
4881 | Dmitry Korchemny |  | normal | trivial | 1800-2012 | 2014-03-09 | 2014-03-11 | Typesetting of sequence methods triggered and matched is inconsistent | new | open | Mehbub | Ben |  | yes |  | nice | 0.1 |  | Errata |  |  | yes
4991 | Erik_Seligman |  | normal | text | 1800-2012 | 2014-08-08 | 2014-08-08 | Need to clarify that clock flow into sampled value functions works just like other sequence ops | new | open | Erik | Samik | yes |  | must |  | 0.2 |  | Clarification |  | yes
5038 | Steven Sharp |  | normal | major | 1800-2012 | 2014-10-07 | 2014-10-07 | Grammar changes for Mantis 3525 appear to have unintended effects | new | open | Anupam | Erik | yes | yes | must | must | 2 |  | Errata |  | yes |  | 5511 is duplicate (Shalom) 5511 has more serious issues with BNF for case endcase property (Anupam)
5056 | Shalom Bresticker |  | normal | text | 1800-2012 | 2014-11-11 | 2014-11-11 | Syntax 16-5 title should be 'Sequence declaration syntax' | new | open | Shalom | Mehbub | yes |  | low |  | 0.1 |  | Errata |  | yes |  | trivial
5194 | Daniel Mlynek |  | normal | text | 1800-2012 | 2015-02-05 | 2015-02-05 | $inferred_clock description should mention checkers and allowed types for $inferred_clock | new | open | Samik | Mehbub
5231 | Dmitry Korchemny |  | normal | major | 1800-2012 | 2015-03-04 | 2015-03-05 | Assertion system tasks are not well-defined for assertions in packages | new | open | Dmitry | Erik | yes | yes | high | high | 3 | 2 | Clarification | Clarification | yes | yes
5248 | Françoise Martinolle |  | normal | minor | 1800-2012 | 2015-03-21 | 2015-03-24 | Clarify the meaning of "function shall be automatic "in section 17.8 and 16.6 | new | open | Shalom | Samik | yes |  | high |  |  |  | Clarification |  | no |  | related to 2928 and 3625, all should be treated at the same time by BC or EC.
5302 | Daniel Mlynek |  | normal | text | 1800-2012 | 2015-05-20 | 2015-05-20 | In some definition of module_or_generate_item_declaration there is lack of default disable | new | open | Samik | Shalom |  | yes |  | high |  | 1 |  | Errata |  | yes | Trivial amount of work
5372 | Erik Seligman |  | normal | text | 1800-2012 | 2015-07-22 | 2015-12-16 | Need to clearly define the term "tick" before using | new | open | Erik | Shalom | yes | yes | high | nice | 0.1 | 1 | Clarification | Clarification | yes | yes | Easy
5438 | Ben Cohen |  | normal | minor | 1800-2012 | 2015-09-17 | 2015-12-16 | TYPO: Example has reference to an undeclared variable + missing () | new | open | Ben | Mehbub | yes |  | high |  | 0.1 |  | Errata |  | yes
5510 | Dmitry Korchemny |  | normal | text |  | 2015-12-13 | 2015-12-14 | Definition of sequential property is awkward | new | open | Dmitry | Ben | yes | yes | high | high | 0.5 | 4 | Clarification | Clarification | yes
5511 | Manisha Kulshrestha |  | high | major | 1800-2011 | 2015-12-17 | 2015-12-21 | property_case_item syntax causes conflicts | new | open | Manisha | Shalom | yes | yes | must | must |  |  |  | Errata | yes | yes | duplicates 5038 (Shalom) Need a proposal based on general consensus. (Manisha) Liable to be a lot of work (Shalom)