## Sheet1
Updated Sheet with Comments | [14 empty] | Reviewer
Id | Reporter | Assigned To | Status | Resolution | Priority | Severity | Product Version | Category | Date Submitted | Updated | Class | Summary | Fixed in Version | Duplicate ID | Name | Effort | Priority | Comment
751 | Jim Vellenga | Jim Vellenga | assigned | open | normal | feature |  | SV-CC | 2005-06-10 | 2006-11-22 | VPI | vpiPrefix can be a class defn too |  | 0 | Abi
756 | Jim Vellenga |  | assigned | open | normal | feature |  | SV-CC | 2005-06-10 | 2006-11-22 | VPI | vpiExpr of expr? |  | 0 | Abi
1581 | Bassam Tabbara | Bassam Tabbara | assigned | open | normal | text |  | SV-CC | 2006-09-01 | 2006-09-01 | VPI | Immediate assertion VPI diagram needs a special section |  | 0 | Abi
1434 | Françoise Martinolle | Françoise Martinolle | assigned | open | normal | major |  | SV-CC | 2006-04-24 | 2006-04-26 | VPI | Which kind of fork join is not available in VPI (27.9) |  | 0 | Abi
757 | Jim Vellenga | Françoise Martinolle | assigned | open | normal | feature |  | SV-CC | 2005-06-15 | 2006-04-26 | VPI | vpiExtern, vpiDPIExport, and vpiDPIImport have no #define's |  | 0 | Abi
732 | Françoise Martinolle | Françoise Martinolle | assigned | open | normal | feature |  | SV-CC | 2005-05-09 | 2006-02-17 | VPI | Representation of super and this in VPI? |  | 0 | Abi
733 | Jim Vellenga | Jim Vellenga | assigned | open | normal | feature |  | SV-CC | 2005-05-10 | 2005-11-30 | VPI | 27.17 -- inconsistent use of vpiTypedefAlias |  | 0 | Abi
800 | chas | chas | assigned | open | normal | feature |  | SV-CC | 2005-07-14 | 2005-11-09 | VPI | 27.30 clocking blocks could have been modeled using delay devices |  | 0 | Abi
746 | Jim Vellenga |  | new | open | normal | feature |  | SV-CC | 2005-06-07 | 2005-06-07 | VPI | What is VPI iteration to get typespecs from an instance? |  | 0 | Abi
3094 | chas |  | new | [5 empty] | 2010-05-27 | 2010-05-17 | VPI | Support for Unified Coverage Interoperability Standard |  | 0 | Abi
3011 | doug_warmke | doug_warmke | assigned | open | normal | minor | 1800-2009 | SV-CC | 2010-03-07 | 2010-03-08 | DPI | DPI import tf's need lifetime qualifier |  | 0 | Amit | Small | Medium | Will need some discussion and can be closed
880 | doug_warmke | doug_warmke | assigned | open | normal | tweak |  | SV-CC | 2005-09-06 | 2008-06-03 | DPI | DPI functions should be allowed to return non-small values |  | 0 | Amit | Large | Medium | Non-small values is a large scope and this will need to be discussed. Effort will be large in case canonical formats need to be defined for non-small values when being returned from DPI
2101 | doug_warmke | doug_warmke | assigned | open | normal | minor | P1800-2008/D4 | SV-CC | 2007-10-11 | 2007-10-25 | DPI | svDpiVersion needs to return "1800-2008" |  | 0 | Amit | Trivial | Medium
1343 | doug_warmke | doug_warmke | assigned | open | normal | feature |  | SV-CC | 2006-02-16 | 2006-03-16 | DPI | Wrong unpacked array correspondence between C and SV |  | 0 | Amit | Small | Medium | Important to define the data layout for arrays when they are passed across language boundaries
1231 | doug_warmke | doug_warmke | assigned | open | normal | trivial |  | SV-CC | 2005-12-13 | 2006-02-18 | DPI | Wrong cross reference in DPI Clause 26.2.2 |  | 0 | Amit | Trivial | Low
736 | doug_warmke | doug_warmke | feedback | reopened | normal | minor |  | SV-CC | 2005-05-24 | 2008-05-15 | DPI | More clarifications on DPI string arguments and pass by reference | P1800-2008/D3a | 0 | Amit | Small | Medium
3022 | shalom |  | new | open | normal | text | 1800-2009 | SV-CC | 2010-04-04 | 2010-04-19 | DPI | Annex I import/export reversals |  | 0 | Amit | Trivial | Low
2400 | shalom |  | new | open | normal | minor | P1800-2008/D5 | SV-CC | 2008-06-03 | 2008-06-03 | DPI | small value is unclear and misleading |  | 0 | Amit | Small | Medium
3086 | chas |  | new | [5 empty] | 2010-05-17 | 2010-05-17 | DPI | Improve interaction between DPI and VPI |  | 0 | Amit | Large | High | Inter-operability of VPI and DPI will needed to be analyzed from all possible phases of simulation cycle
3087 | chas |  | new | [5 empty] | 2010-05-17 | 2010-05-17 | DPI | Improve interaction between SystemC, C++ and DPI |  | 0 | Amit | Huge | High | The requirement here is class level inter-operability across three languages. Will need detailed discussion for spec'ing. Also, the scope of this mantis should be split into two. One should be for defining class level inter-operability with C++ or SystemC. The other aspect should be defining simulation semantics for SystemC inter-operability.
2263 | Françoise Martinolle |  | new | open | normal | major |  | SV-CC | 2008-01-30 | 2008-01-30 | VPI | Information model for assignment patters is not efficient |  | 0 | Bassam
2192 | chas |  | new | open | normal | major | P1800-2008/D4 | SV-CC | 2007-11-13 | 2007-11-13 | VPI | Should VPI cause new objs to exist? |  | 0 | Bassam
2154 | chas |  | new | open | urgent | major | P1800-2008/D4 | SV-CC | 2007-10-25 | 2007-10-25 | VPI | Specification should say what happens if you put value with delay to a dynamic object |  | 0 | Bassam
1720 | John Havlicek |  | new | open | normal | minor |  | SV-CC | 2007-01-22 | 2007-10-25 | VPI | vpiNotOp does not distinguish HDL "!" from property "not" |  | 0 | Bassam
1352 | Bassam Tabbara |  | new | open | normal | trivial |  | SV-CC | 2006-02-22 | 2007-10-25 | VPI | VPI 27.37 "Multiclock sequence expression" error |  | 0 | Bassam
789 | chas |  | new | open | normal | feature |  | SV-CC | 2005-06-27 | 2007-10-25 | VPI | 27.27 need to handle tfs connected by name and default values for args |  | 0 | Bassam
459 | chas |  | new | open | normal | major |  | SV-CC | 2005-03-21 | 2007-10-25 | VPI | 32.13 Have we considered the implications of including arrays here? |  | 0 | Bassam
442 | chas |  | new | open | normal | minor |  | SV-CC | 2005-03-20 | 2007-10-25 | VPI | Annex I - Organization? |  | 0 | Bassam
745 | Jim Vellenga |  | new | open | normal | feature |  | SV-CC | 2005-06-07 | 2005-06-07 | VPI | vpiName for SystemVerilog tf call? |  | 0 | Bassam
1653 | Jim Vellenga | Jim Vellenga | assigned | open | normal | feature |  | SV-CC | 2006-10-26 | 2010-04-28 | VPI | Cannot get to class defn from VPI class typespec |  | 0 | Chas
2449 | Jim Vellenga | Jim Vellenga | assigned | open | normal | minor | P1800-2008/D6 | SV-CC | 2008-07-17 | 2008-07-17 | VPI | Should vpiVirtual for constraints always return TRUE? |  | 0 | Chas
2191 | chas | Jim Vellenga | assigned | open | urgent | major | P1800-2008/D4 | SV-CC | 2007-11-13 | 2008-05-14 | VPI | Typed parameters should be clarified in VPI |  | 0 | Chas
1311 | Françoise Martinolle | Jim Vellenga | assigned | open | normal | feature |  | SV-CC | 2006-01-23 | 2008-05-14 | VPI | type parameters VPI model |  | 742 | Chas
1593 | Chuck_Berking | Chuck_Berking | assigned | open | urgent | feature |  | SV-CC | 2006-09-14 | 2008-03-25 | VPI | vpiName property for members of structs and unions |  | 0 | Chas
2015 | Jim Vellenga | Jim Vellenga | assigned | open | urgent | feature | P1800-2008/D3a | SV-CC | 2007-09-04 | 2008-01-30 | VPI | How should cbValueChange callbacks work with nonstatic variables? |  | 0 | Chas
1752 | Jim Vellenga | Jim Vellenga | assigned | open | normal | feature |  | SV-CC | 2007-02-28 | 2007-11-20 | VPI | Clarify vpiFile and vpiLineNo in general |  | 0 | Chas
486 | chas | Sachchidananda_Patel | assigned | open | normal | minor |  | SV-CC | 2005-03-21 | 2007-10-25 | VPI | 32.34 Why are variables of property spec special? |  | 0 | Chas
484 | chas | Françoise Martinolle | assigned | open | normal | major |  | SV-CC | 2005-03-21 | 2007-10-25 | VPI | 27.28 and 27.29 Should not define callbacks in notes |  | 0 | Chas
480 | chas | michael_rohleder | assigned | open | normal | minor |  | SV-CC | 2005-03-21 | 2007-10-25 | VPI | 27.26 use of vpiRefObj here but not in 27.12 |  | 0 | Chas
463 | chas |  | assigned | open | normal | major |  | SV-CC | 2005-03-21 | 2007-10-25 | VPI | 27.16 should not perpetuate unused functionality |  | 0 | Chas
727 | Bassam Tabbara |  | new | open | normal | feature |  | SV-CC | 2005-05-06 | 2005-05-06 | VPI | Review constraint of 32.23 |  | 0 | Chas
2381 | Abigail Moorhouse |  | new | open | low | trivial | P1800-2008/D5 | SV-CC | 2008-05-07 | 2008-05-07 | VPI | vpiFullName property missing in 36.2 explanatory text |  | 0 | Chuck
2359 | Jim Vellenga |  | new | open | low | trivial | P1800-2008/D4 | SV-CC | 2008-04-10 | 2008-04-10 | VPI | Example (Traversing expressions) should use vpiType instead of vpiExpr |  | 0 | Chuck
2355 | Chuck_Berking |  | new | open | normal | minor | P1800-2008/D4 | SV-CC | 2008-04-09 | 2008-04-09 | VPI | Specify what the effect of a vpi_put_value[_array] on a net/element is when a force is active on it. |  | 0 | Chuck
2354 | Jim Vellenga |  | new | open | normal | minor | P1800-2008/D4 | SV-CC | 2008-04-09 | 2008-04-09 | VPI | Disambiguate which iteration the VPI case detail refers to |  | 0 | Chuck
2346 | Chuck_Berking |  | new | open | normal | minor | P1800-2008/D4 | SV-CC | 2008-04-03 | 2008-04-03 | VPI | Desc. of value chg CB behavior on arrays for vpi_register_cb will need to be reinstated and revised. |  | 0 | Chuck
2332 | Jim Vellenga |  | new | open | normal | feature | P1800-2008/D4 | SV-CC | 2008-03-19 | 2008-03-19 | VPI | Expressions as statements and statements as expressions in VPI |  | 0 | Chuck
2298 | Jim Vellenga |  | new | open | normal | feature | P1800-2008/D4 | SV-CC | 2008-02-29 | 2008-02-29 | VPI | Need VPI object for last element token in queue index expressions |  | 0 | Chuck
2290 | Françoise Martinolle |  | new | open | normal | major | P1800-2008/D4 | SV-CC | 2008-02-25 | 2008-02-26 | VPI | add signal valued system function modeling in VPI |  | 0 | Chuck
749 | Jim Vellenga |  | new | open | normal | feature |  | SV-CC | 2005-06-09 | 2005-06-10 | VPI | vpiParent for constraint? |  | 0 | Chuck
3092 | chas |  | new |  |  |  | 1800-2009 |  | 2010-05-17 | 2010-05-17 | VPI | Need efficient mechanism for tracking aggregate value changes |  | 0 | Chuck
3072 | Bassam Tabbara |  | new | open | normal | feature | 1800-2009 | SV-CC | 2010-05-10 | 2010-05-10 | VPI | VPI for covergroup |  | 0 | Francoise
68 | Bassam Tabbara |  | new | open | normal | minor |  | SV-CC | 2004-07-23 | 2010-02-11 | VPI | VPI access to assertion local variables |  | 0 | Francoise
1112 | Karen Pieper |  | new | open | normal | feature |  | SV-CC | 2005-12-04 | 2010-02-09 | VPI | Attributes in VPI but not in BNF (26.6.42 vs Appendix A) |  | 0 | Francoise
57 | Françoise Martinolle |  | new | open | normal | feature |  | SV-CC | 2004-07-23 | 2008-11-23 | VPI | VPI cannot access the dependent packages for a given instance |  | 0 | Francoise
2240 | Françoise Martinolle |  | new | open | normal | major | P1800-2008/D4 | SV-CC | 2008-01-16 | 2008-10-30 | VPI | vpiSize of a string constant |  | 0 | Francoise
2507 | Jim Vellenga |  | new | open | normal | minor | P1800-2009/D7 | SV-CC | 2008-10-24 | 2008-10-26 | VPI | How should VPI represent unbased unsized literals |  | 0 | Francoise
2425 | shalom |  | new | open | normal | minor | P1800-2008/D6 | SV-CC | 2008-06-23 | 2008-06-23 | VPI | Use of 'reg' in VPI diagrams |  | 0 | Francoise
2393 | Jim Vellenga |  | new | open | normal | minor | P1800-2008/D5 | SV-CC | 2008-05-21 | 2008-05-21 | VPI | Ambiguous note: vpi_iterate() for the default case item |  | 0 | Francoise
3089 | chas |  | new |  |  |  | 1800-2009 |  | 2010-05-17 | 2010-05-17 | VPI | Provide ULM version of VPI data model |  | 0 | Francoise
2068 | Jim Vellenga |  | new | open | normal | feature | P1800-2008/D3a | SV-CC | 2007-10-01 | 2007-10-01 | VPI | Cannot represent interface as vpiHighConn of port |  | 0 | Ghassan
2065 | Jim Vellenga |  | new | open | normal | feature | P1800-2008/D3a | SV-CC | 2007-09-28 | 2007-09-29 | VPI | How should VPI represent statements that are expressions and vice versa? |  | 0 | Ghassan
2064 | Jim Vellenga |  | new | open | normal | feature | P1800-2008/D3a | SV-CC | 2007-09-28 | 2007-09-29 | VPI | How should VPI handle void functions and function calls? |  | 0 | Ghassan
2062 | Abigail Moorhouse |  | new | open | normal | minor | P1800-2008/D3a | SV-CC | 2007-09-27 | 2007-09-27 | VPI | 36.15: Request clarification for the VPI strength properties of a net, vpiStrength0 and vpiStrength1 |  | 0 | Ghassan
2058 | Françoise Martinolle |  | new | open | normal | major | P1800-2008/D3a | SV-CC | 2007-09-26 | 2007-09-26 | VPI | Diagram 36.25 Class definition - vpiDerivedClasses |  | 0 | Ghassan
2042 | Françoise Martinolle |  | new | open | normal | major | P1800-2008/D3a | SV-CC | 2007-09-17 | 2007-09-17 | VPI | Use of strings in DPI/VPI and Dumpvars sections |  | 0 | Ghassan
2034 | Jim Vellenga |  | new | open | normal | feature | P1800-2008/D3a | SV-CC | 2007-09-13 | 2007-09-13 | VPI | sv_vpi_user.h lacks vpiChandleVar and vpiChandleTypespec |  | 0 | Ghassan
753 | Jim Vellenga |  | new | open | normal | feature |  | SV-CC | 2005-06-10 | 2007-09-09 | VPI | No VPI object for an iterative constraint |  | 0 | Ghassan
740 | Jim Vellenga |  | new | open | normal | feature |  | SV-CC | 2005-06-01 | 2005-06-01 | VPI | Does vpiIsProtected apply to a vpiClassObj? |  | 0 | Ghassan
3090 | chas |  | new |  |  |  | 1800-2009 |  | 2010-05-17 | 2010-05-17 | VPI | Create VPI data model extensions for Checkers |  | 0 | Ghassan
450 | chas | Françoise Martinolle | assigned | open | normal | minor |  | SV-CC | 2005-03-21 | 2007-10-25 | VPI | 32.7 confusing note |  | 0 | Jim | Small | Low | Could be a little more precise about aliases, perhaps
436 | chas | Jim Vellenga | assigned | open | normal | major |  | SV-CC | 2005-03-20 | 2007-10-25 | VPI | 30.4.3 is inconsistent with the diagrams in section 32 |  | 0 | Jim | Large | Low | Section 40 is pretty separate, actually
429 | chas |  | assigned | open | normal | major |  | SV-CC | 2005-03-20 | 2007-10-25 | VPI | Need a separate section on VPI routines |  | 0 | Jim | Medium | Low | 39.3.1 really is redundant...
306 | Françoise Martinolle | Françoise Martinolle | assigned | open | normal | feature |  | SV-CC | 2004-11-17 | 2007-10-25 | VPI | vpi_put_value is not defined for systemVerilog datatypes |  | 0 | Jim | Trivial | Low | Can be considered done.
305 | Françoise Martinolle | Françoise Martinolle | assigned | open | normal | feature |  | SV-CC | 2004-11-17 | 2007-10-25 | VPI | vpi_get_value behaviour is not defined for systemVerilog datatypes |  | 0 | Jim | Trivial | Low | Can be considered done.
744 | Jim Vellenga | Jim Vellenga | assigned | open | normal | feature |  | SV-CC | 2005-06-07 | 2007-10-19 | VPI | Does vpiMethods iteration include built-in functions and tasks? |  | 0 | Jim | Trivial | Low | Duplicate of 2094
1652 | Jim Vellenga | Jim Vellenga | assigned | open | normal | feature |  | SV-CC | 2006-10-26 | 2007-10-19 | VPI | Which VPI class defn does a data member class var refer to? |  | 0 | Jim | Trivial | Low | Duplicate of 2094
788 | chas | chas | assigned | open | normal | feature |  | SV-CC | 2005-06-27 | 2007-06-04 | VPI | Should we return vpiOtherFunc for vpiFuncType when on a void function? |  | 0 | Jim | Small | Medium | Proposal already attache
750 | Jim Vellenga |  | new | open | normal | feature |  | SV-CC | 2005-06-10 | 2005-06-10 | VPI | In VPI, constraint from class defn differs from constraint in class obj |  | 0 | Jim | Medium | Medium
3095 | chas |  | new | [5 empty] | 2010-05-17 | 2010-05-17 | VPI | Better defined handling of unnamed objects |  | 0 | Jim | Medium | Medium
430 | chas |  | new | open | normal | major |  | SV-CC | 2005-03-20 | 2007-10-25 | VPI | 29.5.1 Use vpi_remove_cb() to remove callbacks |  | 0 | Michael | Small | Low | In 2009, I think this is 39.5.1: basically need to fix description of vpi_control (38.4) and clarify correct usage for adding/removing callbacks. Actually the same is true for 40.5.4
424 | chas |  | new | open | normal | major |  | SV-CC | 2005-03-20 | 2007-10-25 | VPI | 29.3.1 Should this be here? |  | 0 | Michael | Small | Low | In 2009, this is 39.3.1: simple decision where to move examples
421 | chas |  | new | open | normal | major |  | SV-CC | 2005-03-20 | 2007-10-25 | VPI | 29 - This section should be folded into Section 32 |  | 0 | Michael | Trivial | Low | Description is very sparse -- I am confused, sorry (no idea to which version this relates ...). Suggest to close/reject
378 | chas |  | new | open | normal | feature |  | SV-CC | 2005-02-09 | 2007-10-25 | VPI | Descriptions should include when the order is important |  | 0 | Michael | Medium | Low | Review activitiy, not sure how to cover/represent the information itself
374 | chas |  | new | open | normal | feature |  | SV-CC | 2005-02-09 | 2007-10-25 | VPI | Should be better way of knowing the return values for many properties |  | 0 | Michael | Medium | Medium | Very useful information, need to identify best way to represent this information
351 | Sachchidananda_Patel |  | new | open | normal | feature |  | SV-CC | 2005-01-11 | 2007-10-25 | VPI | putting values at ROsync time |  | 0 | Michael | Medium | Low | Since PLI 1.0 is deprecated, not sure we really need to do this ? Or do we want to widen this up to the new scheduling semantics ???
2139 | Jim Vellenga |  | new | open | normal | feature | P1800-2008/D4 | SV-CC | 2007-10-19 | 2007-10-19 | VPI | Obtaining members of superclasses of vpiClassObj |  | 0 | Michael | Small | Medium | Clarification
2082 | Jim Vellenga |  | new | open | normal | feature | P1800-2008/D3a | SV-CC | 2007-10-05 | 2007-10-05 | VPI | How should we handle vpiSize for multidimensional arrays with mixed static and dynamic ranges? |  | 0 | Michael | Medium | Medium | Clarification, but will require some discussion
2307 | shalom |  | new | [5 empty] | 2008-03-10 | 2008-05-08 | BC | 0002307: Master issue for SV-BC VCD issues |  | 0 | Michael | Large | High | Two basic questions: a) do want to pursue a Reader API or a VCD extension b) items covered by this master issue are SV-BC or SV-CC (most are SV-BC, I think). For me 0104, 1142 and 1950 are falling DEFINITELY into our realm !!!
2023 | Brad Pierce |  | new | open | normal | minor | P1800-2008/D3a | SV-CC | 2007-09-07 | 2007-09-07 | VPI | typedefs don't construct types (34.5.6) |  | 0 | Steve
2017 | Jim Vellenga |  | new | open | normal | feature | P1800-2008/D3a | SV-CC | 2007-09-04 | 2007-09-04 | VPI | Need vpiClassType for built-in process class |  | 0 | Steve
1784 | Jim Vellenga |  | new | open | normal | feature |  | SV-CC | 2007-04-19 | 2007-08-21 | VPI | Need way for VPI to determine max size of queue |  | 0 | Steve
1862 | Chuck_Berking |  | new | open | normal | text | P1800-2008/D3 | SV-CC | 2007-06-14 | 2007-06-14 | VPI | Key to VPI data model diagrams uses "class" terms in description which are potentially confusing. |  | 0 | Steve
747 | Jim Vellenga |  | new | open | normal | feature |  | SV-CC | 2005-06-07 | 2007-06-04 | VPI | Add common VPI properties to typespecs |  | 0 | Steve
1838 | Jim Vellenga |  | new | open | normal | feature |  | SV-CC | 2007-05-23 | 2007-05-23 | VPI | Finding gen scope for VPI net or net array, etc. |  | 0 | Steve |  |  |  | High
1776 | Jim Vellenga |  | new | open | normal | feature |  | SV-CC | 2007-04-11 | 2007-04-11 | VPI | mipd undefined for VPI port objects |  | 0 | Steve |  |  |  | Medium
1764 | Françoise Martinolle |  | new | open | normal | major |  | SV-CC | 2007-03-19 | 2007-03-19 | VPI | vpi_put_value does not specify the scheduling regions |  | 0 | Steve |  |  |  | Low
741 | Jim Vellenga |  | new | open | normal | feature |  | SV-CC | 2005-06-01 | 2005-06-01 | VPI | File and line number for vpiClassObj? |  | 0 | Steve
3091 | chas |  | new | [5 empty] | 2010-05-17 | 2010-05-17 | VPI | Update IP protection model to reflect changes since 2001 |  | 0 | Steve |  |  |  | Huge
1725 | Bassam Tabbara |  | new | open | normal | feature |  | SV-CC | 2007-01-28 | 2007-01-28 | VPI | VPI support for `inside' operator |  | 0 | Ying-Tsia |  |  |  | Large
1649 | Jim Vellenga |  | new | open | normal | feature |  | SV-CC | 2006-10-24 | 2006-10-24 | VPI | Undefined possibly redundant VPI constraint object types |  | 0 | Ying-Tsia |  |  |  | Medium
1522 | shalom |  | new | open | normal | feature |  | SV-CC | 2006-07-02 | 2006-07-02 | VPI | 1364 Fig 27-1: t_vpi_error_info fields not well defined |  | 0 | Ying-Tsia |  |  |  | Small
1477 | Françoise Martinolle |  | new | open | normal | major |  | SV-CC | 2006-05-16 | 2006-05-16 | VPI | virtual interfaces information model |  | 0 | Ying-Tsia |  |  |  | Trivial
1435 | Françoise Martinolle |  | new | open | normal | major |  | SV-CC | 2006-04-24 | 2006-04-24 | VPI | vpiAccessType property values |  | 0 | Ying-Tsia
1335 | Jim Vellenga |  | new | open | normal | feature |  | SV-CC | 2006-02-14 | 2006-02-14 | VPI | VPI does not distinguish types of distribution weights |  | 0 | Ying-Tsia
1329 | Françoise Martinolle |  | new | open | normal | feature |  | SV-CC | 2006-02-08 | 2006-02-08 | VPI | Section 27.11, note 7 incorrect |  | 0 | Ying-Tsia
1088 | Jim Vellenga |  | new | open | normal | text |  | SV-CC | 2005-11-30 | 2005-11-30 | VPI | 27.17 What exactly is a vpiTypedefAlias? |  | 0 | Ying-Tsia
752 | Jim Vellenga |  | new | open | normal | feature |  | SV-CC | 2005-06-10 | 2005-06-10 | VPI | No way to tell in VPI if method task or function is static |  | 0 | Ying-Tsia
2146 | Jim Vellenga | Bassam Tabbara | assigned | open | urgent | feature | P1800-2008/D4 | SV-CC | 2007-10-24 | 2007-12-24 | Reader API | Data read API description references wrong header file |  | 0
2147 | Jim Vellenga | Bassam Tabbara | assigned | open | urgent | feature | P1800-2008/D4 | SV-CC | 2007-10-24 | 2007-12-03 | Reader API | How does data read API handle dynamically allocated objects? |  | 0
2145 | Jim Vellenga | Bassam Tabbara | assigned | open | urgent | feature | P1800-2008/D4 | SV-CC | 2007-10-24 | 2007-10-25 | Reader API | In data read API, values used for time types are not suitable for bit masking |  | 0
2144 | Jim Vellenga | Bassam Tabbara | assigned | open | urgent | feature | P1800-2008/D4 | SV-CC | 2007-10-24 | 2007-10-25 | Reader API | Why does the data read API include traversals for vpiParameters? |  | 0
560 | chas | Bassam Tabbara | assigned | open | urgent | major |  | SV-CC | 2005-03-22 | 2008-01-01 |  | 31.4.1 & 31.4.2.1 Overloading vpi_handle() is a bad idea |  | 0
563 | chas | Bassam Tabbara | assigned | open | urgent | minor |  | SV-CC | 2005-03-22 | 2007-12-31 |  | 31.5 diagram in figure 31-18 needs to be redrawn |  | 0
593 | chas | Bassam Tabbara | assigned | open | urgent | minor |  | SV-CC | 2005-03-23 | 2007-12-31 |  | 31.12 Routines should be in table format |  | 0
2148 | Jim Vellenga | Bassam Tabbara | assigned | open | urgent | minor | P1800-2008/D4 | SV-CC | 2007-10-24 | 2007-12-28 |  | Unclear statement about error handling after calling vpi_unload() |  | 0
568 | chas | Bassam Tabbara | assigned | open | urgent | major |  | SV-CC | 2005-03-22 | 2007-12-28 |  | 31.8.1 initialization and loading functionality is optional? |  | 0
580 | chas | Bassam Tabbara | assigned | open | urgent | minor |  | SV-CC | 2005-03-23 | 2007-12-28 |  | 31.8.4 section is not necessary and colloquial |  | 0
581 | chas | Bassam Tabbara | assigned | open | urgent | minor |  | SV-CC | 2005-03-23 | 2007-12-28 |  | 31.8.4.1 Need to clarify the first paragraph |  | 0
573 | chas | Bassam Tabbara | assigned | open | urgent | major |  | SV-CC | 2005-03-22 | 2007-12-28 |  | 31 superfluous functionality added in the name of performance |  | 0
562 | chas | Bassam Tabbara | assigned | open | urgent | minor |  | SV-CC | 2005-03-22 | 2007-12-28 |  | 31.5 needless restriction on traverse object creation - poor terminology |  | 0
556 | chas | Bassam Tabbara | assigned | open | urgent | major |  | SV-CC | 2005-03-22 | 2007-12-25 |  | 31.2 Beginning of this section not needed in larger context of spec |  | 0
557 | chas | Bassam Tabbara | assigned | open | urgent | minor |  | SV-CC | 2005-03-22 | 2007-12-25 |  | 31.3.1 specific references to objects should be removed |  | 0
558 | chas | Bassam Tabbara | assigned | open | urgent | minor |  | SV-CC | 2005-03-22 | 2007-12-25 |  | 31.3.3 rename section to "Access availability" |  | 0
555 | chas | Bassam Tabbara | assigned | open | urgent | major |  | SV-CC | 2005-03-22 | 2007-12-25 |  | 31.1 Introduction not needed in context of the larger document |  | 0
565 | chas | Bassam Tabbara | assigned | open | urgent | minor |  | SV-CC | 2005-03-22 | 2007-12-25 |  | 31.6 remove first paragraph of this section |  | 0
584 | chas | Bassam Tabbara | assigned | open | urgent | minor |  | SV-CC | 2005-03-23 | 2007-12-25 |  | 31.8.4.2 implies that vpi_goto() creates new handle |  | 0
572 | chas | Bassam Tabbara | assigned | open | urgent | minor |  | SV-CC | 2005-03-22 | 2007-12-24 |  | 31.8 make use of the term 'user' |  | 0
571 | chas | Bassam Tabbara | assigned | open | urgent | minor |  | SV-CC | 2005-03-22 | 2007-12-24 |  | 31.8.1 unnecessary complication added for vpi_close() |  | 0
570 | chas | Bassam Tabbara | assigned | open | urgent | minor |  | SV-CC | 2005-03-22 | 2007-12-24 |  | 31.8.1 Need prototype for vpi_load_extension() |  | 0
583 | chas | Bassam Tabbara | assigned | open | urgent | minor |  | SV-CC | 2005-03-23 | 2007-12-24 |  | 31.8.4.2 terminology first defined in a footnote? |  | 0
561 | chas | Bassam Tabbara | assigned | open | urgent | minor |  | SV-CC | 2005-03-22 | 2007-12-24 |  | 31.4.2 vpi_free_object() should be explicitly referenced here |  | 0
592 | chas | Bassam Tabbara | assigned | open | urgent | minor |  | SV-CC | 2005-03-23 | 2007-10-25 |  | 31.12 return values for functions is backwards |  | 0
590 | chas | Bassam Tabbara | assigned | open | urgent | major |  | SV-CC | 2005-03-23 | 2007-10-25 |  | 31.10 Should provide dlopen() like functionality |  | 0
589 | chas | Bassam Tabbara | assigned | open | urgent | minor |  | SV-CC | 2005-03-23 | 2007-10-25 |  | 31.10 cannot set the user_data field |  | 0
579 | chas | Bassam Tabbara | assigned | open | urgent | major |  | SV-CC | 2005-03-23 | 2007-10-25 |  | 31.8.3.2 This section should be replaced with a object model diagram |  | 0
567 | chas | Bassam Tabbara | assigned | open | urgent | major |  | SV-CC | 2005-03-22 | 2007-10-25 |  | 31.7 arbitrary overloading of the routines |  | 0
559 | chas | Bassam Tabbara | assigned | open | urgent | minor |  | SV-CC | 2005-03-22 | 2007-10-25 |  | 31.4.2 Only need one collection type |  | 0