## svecTOP25_Nov2011
ranking in top25 | state | Id | Summary | assigned | P1800-2012 Drafts | Comments
4 | feedback | 1356 | Multiple Inheritance | Brandon |  | Updated 11/19/2011 1356_Interface_Classes_rev16.pdf
21 | feedback | 2506 (2953) | Non-trivial coverage space shapes and joint conditions are difficult to specify with covergroups (replace 2953 Algorithmic generation of covergroup bin contents) | Scott |  | Proposal for Mantis 2506_v14.pdf
9 | resolved | 2845 | virtual interface type checking versus interface type that had been defparam'ed | Francoise |  | champions approved 11/17/2011
11 | resolved | 2505 | class select: what is allowed after the dot? | Neil S. |  | champions approved 11/17/2011 SV_LRM_Mantis2505v8.pdf
25 | resolved | 2987 | Soft Constraints | Arturo |  | editor needs to make changes. Mantis2987_SoftConstraintsProposal_v7.pdf
| resolved | 3278 | (related to 1356) virtual method type rules | Francoise |  | 3278-v6.pdf The proposal modifies subclause 8.19. In Draft 3, this has changed to be 8.20. The Editor has agreed to make this change when the proposal is implemented.
16 | Approved | 3028 | constraints for unique array elements. | Jonathan |  | approved on 11/10/2011 proposal-3028-3.pdf
3 | completed | 3046 | Dotted names within inlined constraints | Gordon | D3 | 3046_inline_dotted_names_rev3.pdf
15 | completed | 2112 | Remove restrictions on NBA assigments to class members | Dave | D3 | 2112_NBA_v6.pdf
18 | completed | 2794 | Clarify queue methods return status | Jonathan | D3 | proposal-2794-v4.pdf
| completed | 3293 | (related to 1356) Clarify $cast behaviour on class handles | Jonathan | D3 | changes updated 3293-proposal_v5.pdf
5 | editor | 3001 | Proper Polymorphic behavior of instantiation | Jonathan |  | proposal-3001-4.pdf The implementation of the proposal is consistent with the concern that Shalom raised in note 0012341. The word "extends" should be in a different font in that sentence.
17 | editor | 2950 | virtual method prototype matching | Francoise | D1 | Checked in D1, editor state for updates " virtual should be in bold" ( 2950.pdf)
10 | completed | 2956 | clarify class 'process' definition (9.7 vs 18.13.3, 18.13.4, 18.13.5) | Dave | D1 | Proposal2956.pdf
22 | completed | 1349 | fork/join_none: what if parent thread terminates without blocking statement? | Steven | D1 | Proposal 1349.pdf
23 | completed | 2949 | LRM is silent about the semantics of referencing a clocking block output | Jonathan | D1 | proposal-2949-1a.pdf
24 | completed | 2451 | Omitting body defaults | Steven | D1 | Proposal2451v2b.pdf
| closed | 3279 | (related to 1356) Enhance method override rules to allow covariant typing |  |  | Merged in 3278
OTHERS RESOLVED/FIXED during p1800-2012 PAR
| completed | 3254 | 18.5.6 if-else constraints mistakenly uses the work "block" when it means "set" | Dave | D2 | proposal: 3254_constraint_set.pdf
| completed | 2900 | Associative array should consider the context of an lvalue to create an entry | Dave | D3 | a 2900_assoc_lvalue_v4_FA.pdf
| completed | 2905 | BNF bug for attribute instance along with timeunits_declaration | Shalom | D3 | a 2905_attribute_timeunits.pdf
| completed | 3046 | Dotted names within inlined constraints | Gordon | D3 | a 3046_inline_dotted_names_rev3.pdf
| completed | 3719 | Fix editorial errors in Syntax 11-8 and in 38.3 | Stuart | D3 | from 3531 mantis
| completed | 3736 | Error in example for 19.5 Defining coverage point | Ben Cohen | D3 | Mantis0003763Errorinexamplefor19.5Definingcoveragepoint.pdf
| closed | 1091 | Jeda verification enhancements
| closed | 3634 | correct "Re-Active" region to "Reactive" region |  | D2 | P1800-2012/D2
| closed | 3635 | datatype should be "data type" |  | D2 | P1800-2012/D2
| closed | 3585 | #1step is typeset inconsistently in the LRM |  | D2 | P1800-2012/D2
| closed | 2952 | Identifier case error in 25.9 virtual interface example |  | D2 | P1800-2012/D2
| closed | 3181 | incorrect syntax in with clause in example in 18.5.7.2 |  | D2 | P1800-2012/D2
| closed | 3297 | 18.6.2 font size issue |  | D2 | P1800-2012/D2
NOT FIXED
1 | 4 | 2848 | Is it legal to assign an interface containing class declaration to a virtual interface
2 | 12 | 3002 | Aspect Oriented Programming (AOP) features
6 | 3 | 2999 | Class Handle reference inside of Constraints
7 | 5 | 3003 | Constraint Composition
8 | 8 | 3082 | Ambiguity resolution (see slide 10 for examples of parts of the Standard that have been interpreted differently by different simulators) [The first 3 items on page 10, the other 4 on this page are more trivial]
12 | 4 | 2735 | Ballot Comment #48: Chaining of method calls
13 | 1 | 1706 | Meaning of static prefix for virtual interface assignments
14 | 2 | 2488 | Are virtual method calls legal within class constructors?
19 | 4 | 2993 | Cross cover points across different cover groups
20 | 0.5 | 1442 | Clocking blocks legal in modports, missing from text description in 20.9

## svecTOP25_May2010
estimates of hours | top 25 | Id | Number of Votes | weighted vote | Summary | Degrees of difficulty | Cateogory | Sub-Category | Degrees of difficulty
4 | 1 | 2848 | 7 | 159 | Is it legal to assign an interface containing class declaration to a virtual interface | med | Virtual Interface and class |  | med
12 | 2 | 3002 | 8 | 125 | Aspect Oriented Programming (AOP) features | High | class | constraints | High
1 | 3 | 3046 | 8 | 112 | Dotted names within inlined constraints | Low | class | Strings/Arrays | Low
16 | 4 | 1356 | 6 | 112 | Multiple Inheritance | High | class | Strings | High
2 | 5 | 3001 | 9 | 102 | Proper Polymorphic behavior of instantiation | low | class | Arrays | low
3 | 6 | 2999 | 7 | 99 | Class Handle reference inside of Constraints | med | class | constraints | med
5 | 7 | 3003 | 6 | 98 | Constraint Composition | High | Randomization | Strings | High
8 | 8 | 3082 | 7 | 96 | Ambiguity resolution (see slide 10 for examples of parts of the Standard that have been interpreted differently by different simulators) [The first 3 items on page 10, the other 4 on this page are more trivial]
4 | 9 | 2845 | 4 | 84 | virtual interface type checking versus interface type that had been defparam'ed | high | Virtual Interface | Misc / function proto | high
0.5 | 10 | 2956 | 4 | 76 | clarify class 'process' definition (9.7 vs 18.13.3, 18.13.4, 18.13.5) | low | Process control |  | low
3 | 11 | 2505 | 4 | 76 | class select: what is allowed after the dot? | low | class |  | low
4 | 12 | 2735 | 4 | 73 | Ballot Comment #48: Chaining of method calls | med | class | constraints | med
1 | 13 | 1706 | 4 | 72 | Meaning of static prefix for virtual interface assignments |  | Virtual Interfaces
2 | 14 | 2488 | 4 | 69 | Are virtual method calls legal within class constructors? | med | VI OO classes |  | med
2 | 15 | 2112 | 6 | 69 | Remove restrictions on NBA assigments to class members | med | class | constraints | med
2 | 16 | 3028 | 6 | 68 | constraints for unique array elements. | Med | Randomization |  | Med
2 | 17 | 2950 | 4 | 67 | virtual method prototype matching | low | class |  | low
1 | 18 | 2794 | 4 | 64 | Clarify queue methods return status | low | class |  | low
4 | 19 | 2993 | 4 | 63 | Cross cover points across different cover groups | med | Built-in Methods |  | med
0.5 | 20 | 1442 | 3 | 63 | Clocking blocks legal in modports, missing from text description in 20.9 |  | Functional Coverage
6 | 21 | 2953 | 6 | 61 | Algorithmic generation of covergroup bin contents | high | clocking block |  | high
0.5 | 22 | 1349 | 5 | 61 | fork/join_none: what if parent thread terminates without blocking statement? |  | Functional Coverage
0.5 | 23 | 2949 | 4 | 60 | LRM is silent about the semantics of referencing a clocking block output | low | Process control | constraints | low
4 | 24 | 2451 | 6 | 58 | Omitting body defaults | med | clocking block | constraints | med
4 | 25 | 2987 | 6 | 56 | Soft Constraints | med | class | Misc / function proto | med
92 | total | 46 (2hr sessions)
0.5 | 26 | 3006 | 5 | 55 | LRM doesn't say explicitly what should happen if null pointer is randomized | low | class | Data Types | Arrays Q
4 | 27 | 3004 | 5 | 55 | Ability to declare/qualify classes/methods/variables/constraints final | med | class | Virtual Interface
2 | 28 | 2998 | 4 | 55 | Solve Before enhanced | low | Randomization | class
4 | 29 | 2117 | 3 | 52 | Allow extending of covergroups in classes | high | Functional Coverage | class
4 | 30 | No Mantis 6 | 5 | 51 | (3) Allow reuse of enumerated names (slide 31) |  | cross-committee | Randomization | constraints
0.5 | 31 | 2928 | 3 | 50 | ambiguous restriction on function calls in constraint expressions | low | Randomization | Randomization | constraints
4 | 32 | 2787 | 3 | 50 | reference via scope operator to parametrized superclass item | med | class | Randomization | constraints
2 | 33 | 2972 | 3 | 49 | add class constructor/method, task/function overloading | High | class | Randomization | constraints
2 | 34 | 2996 | 4 | 49 | Method overloading | High | class | Randomization | constraints
0 | 35 | 2988 | 2 | 48 | Defaults Constraints | med | Randomization | Process control
0 | 36 | No Mantis 4 | 2 | 47 | (1) AOP when-inheritance (slide 31) |  | Class/AOP | Functional Coverage
23 | total | 11 sessions